## Sheet
Category | Reference | Macro | Priority | Time | Complexity | Resources
Name of the category |  | Subtasks | Priority according to the security risks - Low : Non-priority tasks that do not address a risk but are good practices - Medium : Non-priority tasks that address a minor risk - High : Tasks to be scheduled quickly that involve a risk of partial compromised - Critical : Tasks to be scheduled quickly that involve a risk of total compromised | Estimated implementation - S : <3 days - M : < 1 week - L : < 1,5 week - XL : > 1,5 week These are approximate estimates | Scale from 1 to 4 to evaluate the difficulty of the implementation
ApiGateway | AWS_APG_001 | Export ApiGateways logs to CloudWatch |  |  |  | arn:aws:apigateway:eu-west-1::/restapis/xxi3pqxsq0/stages/release arn:aws:apigateway:eu-west-1::/restapis/64pwsyb1k7/stages/dev arn:aws:apigateway:eu-west-1::/restapis/l4mkgh9f14/stages/prod arn:aws:apigateway:eu-west-1::/restapis/mhx8ntokz0/stages/prod arn:aws:apigateway:eu-west-1::/restapis/qfdli8mkv5/stages/altprod
ApiGateway | AWS_APG_002 | Protect ApiGateways with AWS WAF |  |  |  | arn:aws:apigateway:eu-west-1::/restapis/mhx8ntokz0/stages/prod arn:aws:apigateway:eu-west-1::/restapis/qfdli8mkv5/stages/altprod arn:aws:apigateway:eu-west-1::/restapis/xxi3pqxsq0/stages/release arn:aws:apigateway:eu-west-1::/restapis/64pwsyb1k7/stages/dev arn:aws:apigateway:eu-west-1::/restapis/l4mkgh9f14/stages/prod
ApiGateway | AWS_APG_003 | Enable tracing on ApiGateways |  |  |  | arn:aws:apigateway:eu-west-1::/restapis/l4mkgh9f14/stages/prod arn:aws:apigateway:eu-west-1::/restapis/mhx8ntokz0/stages/prod arn:aws:apigateway:eu-west-1::/restapis/qfdli8mkv5/stages/altprod arn:aws:apigateway:eu-west-1::/restapis/xxi3pqxsq0/stages/release arn:aws:apigateway:eu-west-1::/restapis/64pwsyb1k7/stages/dev
EC2 Snapshot | AWS_BAK_002 | Make daily snapshot for EC2 volumes |  |  |  | arn:aws:ec2:eu-west-1::volume/vol-08fa9d17ed764a043
CloudFront | AWS_CFT_001 | Enforce TLS 1.2 at least on CloudFronts |  |  |  | arn:aws:cloudfront::554360978219:distribution/E29DC59VXMHNI6 arn:aws:cloudfront::554360978219:distribution/E2VOTRQW4AZDDS
CloudFront | AWS_CFT_003 | Enable Standard logging on CloudFronts |  |  |  | arn:aws:cloudfront::554360978219:distribution/EC9HRCCQ67AAN arn:aws:cloudfront::554360978219:distribution/E29DC59VXMHNI6 arn:aws:cloudfront::554360978219:distribution/E2VOTRQW4AZDDS arn:aws:cloudfront::554360978219:distribution/E1LLJ8H6FCP84Y arn:aws:cloudfront::554360978219:distribution/E1K7NAOFZMOUKO arn:aws:cloudfront::554360978219:distribution/E2EKUMVVCQRFBR
CloudFront | AWS_CFT_004 | Enable Cookies logging on CloudFronts |  |  |  | arn:aws:cloudfront::554360978219:distribution/EC9HRCCQ67AAN arn:aws:cloudfront::554360978219:distribution/E29DC59VXMHNI6 arn:aws:cloudfront::554360978219:distribution/E2VOTRQW4AZDDS arn:aws:cloudfront::554360978219:distribution/E1LLJ8H6FCP84Y arn:aws:cloudfront::554360978219:distribution/E1K7NAOFZMOUKO arn:aws:cloudfront::554360978219:distribution/E2EKUMVVCQRFBR
CloudFront | AWS_CFT_005 | Protect CloudFronts with AWS WAF |  |  |  | arn:aws:cloudfront::554360978219:distribution/EC9HRCCQ67AAN arn:aws:cloudfront::554360978219:distribution/E29DC59VXMHNI6 arn:aws:cloudfront::554360978219:distribution/E2VOTRQW4AZDDS arn:aws:cloudfront::554360978219:distribution/E1LLJ8H6FCP84Y arn:aws:cloudfront::554360978219:distribution/E1K7NAOFZMOUKO arn:aws:cloudfront::554360978219:distribution/E2EKUMVVCQRFBR
Cognito | AWS_COG_001 | Disallows unauthenticated users on Cognito |  |  |  | revinaxhandbookd098ed29_identitypool_d098ed29__release revinaxhandbookd098ed29_identitypool_d098ed29__altprod revinaxhandbookd098ed29_identitypool_d098ed29__prod revinaxhandbookd098ed29_identitypool_d098ed29__dev amplifyjsappd6a5857f_identitypool_d6a5857f__prod
DynamoDB | AWS_DYN_001 | Enable encryption on DynamoDB tables |  |  |  | arn:aws:dynamodb:eu-west-1:554360978219:table/accessCodes-prod arn:aws:dynamodb:eu-west-1:554360978219:table/categories-altprod arn:aws:dynamodb:eu-west-1:554360978219:table/categories-prod ... and 11 more
EC2 | AWS_EC2_001 | Limit public IP on EC2 instances |  |  |  | arn:aws:ec2:eu-west-1::instance/i-06c92177c654f4040
EC2 | AWS_EC2_002 | Enable monitoring on EC2 instances |  |  |  | arn:aws:ec2:eu-west-1::instance/i-06c92177c654f4040
Intrusion Detection | AWS_GDT_001 | Enable and configure GuardDuty for intrusion detection
IAM | AWS_IAM_001 | Enforce 2FA on AWS account |  |  |  | arn:aws:iam::554360978219:user/matthieu-bachelier arn:aws:iam::554360978219:user/oussama-padok arn:aws:iam::554360978219:user/production-data-archiver ... and 5 more
IAM | AWS_IAM_002 | Rotate Access Keys every 90 days |  |  |  | arn:aws:iam::554360978219:user/matthieu-bachelier arn:aws:iam::554360978219:user/production-data-archiver arn:aws:iam::554360978219:user/revinax-admin ... and 8 more
IAM | AWS_IAM_004 | Follow principle of least privilege for IAM Roles |  |  |  | arn:aws:iam::554360978219:role/k8rmf2k-7fc661i arn:aws:iam::554360978219:role/revinax-handbook-admin arn:aws:iam::554360978219:role/lamdbaRoleStephTest ... and 6 more
IAM | AWS_IAM_005 | Remove unused IAM users |  |  |  | arn:aws:iam::554360978219:user/matthieu-bachelier arn:aws:iam::554360978219:user/production-data-archiver arn:aws:iam::554360978219:user/revinax-nas ... and 5 more
Lambda | AWS_LMD_001 | Configure Lambda functions inside a VPC |  |  |  | arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-release arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-mast-UserPoolClientLambda-118XQHTQALWPH arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-master ... and 54 more
Lambda | AWS_LMD_002 | Configure Security Group for Lambda functions |  |  |  | arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-release arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-mast-UserPoolClientLambda-118XQHTQALWPH arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-master ... and 54 more
Bucket | AWS_S3_001 | Enable encryption on S3 buckets |  |  |  | arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment ... and 51 more
Bucket | AWS_S3_002 | Create S3 buckets in only on zone |  |  |  | arn:aws:s3:::5a2i1c-hwk8prd arn:aws:s3:::aj06h6a-reepgie arn:aws:s3:::amplify-nextjstest-dev-110302-deployment ... and 8 more
Bucket | AWS_S3_003 | Enable versioning on S3 buckets |  |  |  | arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment ... and 63 more
Bucket | AWS_S3_004 | Set retention policy on S3 buckets |  |  |  | arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment ... and 65 more
Volume | AWS_VOL_001 | Enable encryption on EC2 volumes |  |  |  | arn:aws:ec2:eu-west-1::volume/vol-08fa9d17ed764a043
Volume | AWS_VOL_002 | Use GP3 for EC2 volumes |  |  |  | arn:aws:ec2:eu-west-1::volume/vol-08fa9d17ed764a043
Volume | AWS_VOL_003 | Create snapshot for EC2 volumes |  |  |  | arn:aws:ec2:eu-west-1::volume/vol-08fa9d17ed764a043
VPC | AWS_VPC_004 | Enable VPC Flow Logs |  |  |  | arn:aws:ec2:eu-west-1::vpc/vpc-6d6a760b

## AWS_DYN_001
Enable encryption on DynamoDB tables
arn:aws:dynamodb:eu-west-1:554360978219:table/accessCodes-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/categories-altprod
arn:aws:dynamodb:eu-west-1:554360978219:table/categories-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/categories-release
arn:aws:dynamodb:eu-west-1:554360978219:table/experiences-altprod
arn:aws:dynamodb:eu-west-1:554360978219:table/experiences-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/experiences-release
arn:aws:dynamodb:eu-west-1:554360978219:table/organizations-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/sponsorships-altprod
arn:aws:dynamodb:eu-west-1:554360978219:table/sponsorships-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/sponsorships-release
arn:aws:dynamodb:eu-west-1:554360978219:table/users-altprod
arn:aws:dynamodb:eu-west-1:554360978219:table/users-prod
arn:aws:dynamodb:eu-west-1:554360978219:table/users-release

## AWS_IAM_001
Enforce 2FA on AWS account
arn:aws:iam::554360978219:user/matthieu-bachelier
arn:aws:iam::554360978219:user/oussama-padok
arn:aws:iam::554360978219:user/production-data-archiver
arn:aws:iam::554360978219:user/revinax-nas
arn:aws:iam::554360978219:user/revinax-ses-smtp
arn:aws:iam::554360978219:user/revinax-website-b2b
arn:aws:iam::554360978219:user/revinax-website-b2c
arn:aws:iam::554360978219:user/thibault-padok

## AWS_IAM_002
Rotate Access Keys every 90 days
arn:aws:iam::554360978219:user/matthieu-bachelier
arn:aws:iam::554360978219:user/production-data-archiver
arn:aws:iam::554360978219:user/revinax-admin
arn:aws:iam::554360978219:user/revinax-ses-smtp
arn:aws:iam::554360978219:user/revinax-website-b2b
arn:aws:iam::554360978219:user/revinax-website-b2c
arn:aws:iam::554360978219:user/stephane-saffre
arn:aws:iam::554360978219:user/sulliman-abdul
arn:aws:iam::554360978219:user/teddy-vataire
arn:aws:iam::554360978219:user/tom-maineult
arn:aws:iam::554360978219:user/tom-maineult

## AWS_IAM_004
Follow principle of least privilege for IAM Roles
arn:aws:iam::554360978219:role/k8rmf2k-7fc661i
arn:aws:iam::554360978219:role/revinax-handbook-admin
arn:aws:iam::554360978219:role/lamdbaRoleStephTest
arn:aws:iam::554360978219:role/eu-west-1_L9VGkwq8g_Full-access
arn:aws:iam::554360978219:role/amplifyconsole-backend-role
arn:aws:iam::554360978219:role/eoektul-dztzote
arn:aws:iam::554360978219:role/RevinaxHandbookGlueExtractDynamoDBUsersTable
arn:aws:iam::554360978219:role/ndzhmyr-5lm35da
arn:aws:iam::554360978219:role/RevinaxHandbookGlueETLJob

## AWS_IAM_005
Remove unused IAM users
arn:aws:iam::554360978219:user/matthieu-bachelier
arn:aws:iam::554360978219:user/production-data-archiver
arn:aws:iam::554360978219:user/revinax-nas
arn:aws:iam::554360978219:user/revinax-ses-smtp
arn:aws:iam::554360978219:user/revinax-website-b2b
arn:aws:iam::554360978219:user/revinax-website-b2c
arn:aws:iam::554360978219:user/sulliman-abdul
arn:aws:iam::554360978219:user/tom-maineult

## AWS_LMD_001
Configure Lambda functions inside a VPC
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-release
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-mast-UserPoolClientLambda-118XQHTQALWPH
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-master
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-EZQLGY6PMR2H
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaContact-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-master
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-custom-message-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-3795X922S78Y
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLocales-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-verify-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-RAYMUS624IPN
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLocales-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-create-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-amplify-js-app-prod-1-UserPoolClientLambda-11XEO8FROBC8U
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaDailyClean-dev
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaDailyClean-prod
arn:aws:lambda:eu-west-1:554360978219:function:hello-prod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-master
arn:aws:lambda:eu-west-1:554360978219:function:revinax-dynamodb-catalog
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-release
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-define-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-rele-UserPoolClientLambda-15C94X3KB5XNG
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUsers-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-altp-UserPoolClientLambda-1T2QOHK0WGJP1
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaContact-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-amplify-js-app-pr-UpdateRolesWithIDPFuncti-IBCIEKI88OR7
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-altprod

## AWS_LMD_002
Configure Security Group for Lambda functions
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-release
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-mast-UserPoolClientLambda-118XQHTQALWPH
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-master
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-EZQLGY6PMR2H
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaContact-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-master
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-custom-message-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-3795X922S78Y
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLocales-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-verify-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-UpdateRolesWithIDPFuncti-RAYMUS624IPN
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSponsorships-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLocales-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-create-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-amplify-js-app-prod-1-UserPoolClientLambda-11XEO8FROBC8U
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaDailyClean-dev
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaDailyClean-prod
arn:aws:lambda:eu-west-1:554360978219:function:hello-prod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-master
arn:aws:lambda:eu-west-1:554360978219:function:revinax-dynamodb-catalog
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUser-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-release
arn:aws:lambda:eu-west-1:554360978219:function:amplify-login-define-auth-challenge-e1bd8b13
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSignup-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaVerifyAccount-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCategories-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaSubscription-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaForgot-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-rele-UserPoolClientLambda-15C94X3KB5XNG
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogout-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaUsers-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-revinax-handbook-altp-UserPoolClientLambda-1T2QOHK0WGJP1
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaContact-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-altprod
arn:aws:lambda:eu-west-1:554360978219:function:amplify-amplify-js-app-pr-UpdateRolesWithIDPFuncti-IBCIEKI88OR7
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaLogin-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaExperiences-release
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-altprod
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaPostConfirmation-master
arn:aws:lambda:eu-west-1:554360978219:function:revinaxLambdaCustomMessage-altprod

## AWS_S3_001
Enable encryption on S3 buckets
arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment
arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment
arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment
arn:aws:s3:::amplify-js-app-data
arn:aws:s3:::amplify-js-app-dataapp-dev
arn:aws:s3:::amplify-js-app-dataapp-prod
arn:aws:s3:::amplify-revinax-handbook-altprod-161543-deployment
arn:aws:s3:::amplify-revinax-handbook-master-161045-deployment
arn:aws:s3:::amplify-revinax-handbook-release-194445-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-115624-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-150330-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-153209-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163753-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163815-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-165959-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-170653-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-101216-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-113921-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-114813-deployment
arn:aws:s3:::authhandbookverificationbucket-dev
arn:aws:s3:::aws-athena-query-results-eu-west-1-554360978219
arn:aws:s3:::aws-cloudtrail-logs-554360978219-3a8b3014
arn:aws:s3:::aws-cloudtrail-logs-554360978219-f7b6fe5a
arn:aws:s3:::aws-glue-assets-554360978219-eu-west-1
arn:aws:s3:::aws-glue-scripts-554360978219-eu-west-1
arn:aws:s3:::aws-glue-temporary-554360978219-eu-west-1
arn:aws:s3:::revinax-data-shared
arn:aws:s3:::revinax-handbook-backup
arn:aws:s3:::revinax-handbook-data
arn:aws:s3:::revinax-handbook-data-altprod
arn:aws:s3:::revinax-handbook-data-backup
arn:aws:s3:::revinax-handbook-data-release
arn:aws:s3:::revinax-handbook-data-shared
arn:aws:s3:::revinax-handbook-reports
arn:aws:s3:::revinax-handbook-web-serverless-dev
arn:aws:s3:::revinax-handbook-web-serverless-prod
arn:aws:s3:::revinax-webapp-dev-20191007150241-deployment
arn:aws:s3:::revinax-webapp-dev-20191007150522-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151319-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151419-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152232-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152434-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152734-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152924-deployment
arn:aws:s3:::revinax-webapp-prod-20191011151758-deployment
arn:aws:s3:::revinax-webapp-prod-20191011152156-deployment
arn:aws:s3:::revinax-webapp-prod-20191011172617-deployment
arn:aws:s3:::revinaxauthverificationbucket-dev
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-altprod
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-master
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-release
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-staging
arn:aws:s3:::revinaxwebapp60aee946verificationbucket-prod
arn:aws:s3:::share2.revinax.net

## AWS_S3_002
Create S3 buckets in only on zone
arn:aws:s3:::5a2i1c-hwk8prd
arn:aws:s3:::aj06h6a-reepgie
arn:aws:s3:::amplify-nextjstest-dev-110302-deployment
arn:aws:s3:::bgku0m-7coegfa
arn:aws:s3:::e3vaktn-0sdwox4
arn:aws:s3:::eoektul-fb6p35o
arn:aws:s3:::fvgm3o-p57plrp
arn:aws:s3:::j3xuf2-482stmr
arn:aws:s3:::kparto3-76wcyh
arn:aws:s3:::revinax-production-data-archive
arn:aws:s3:::vbumvy8-ple2zm9l

## AWS_S3_003
Enable versioning on S3 buckets
arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment
arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment
arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment
arn:aws:s3:::amplify-amplifytest-dev-150111-deployment
arn:aws:s3:::amplify-js-app-data
arn:aws:s3:::amplify-js-app-dataapp-dev
arn:aws:s3:::amplify-js-app-dataapp-prod
arn:aws:s3:::amplify-revinax-handbook-altprod-161543-deployment
arn:aws:s3:::amplify-revinax-handbook-dd-174702-deployment
arn:aws:s3:::amplify-revinax-handbook-dev-161708-deployment
arn:aws:s3:::amplify-revinax-handbook-master-161045-deployment
arn:aws:s3:::amplify-revinax-handbook-prod-140109-deployment
arn:aws:s3:::amplify-revinax-handbook-release-194445-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-115624-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-150330-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-153209-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163753-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163815-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-165959-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-170653-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-101216-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-113921-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-114813-deployment
arn:aws:s3:::authhandbookverificationbucket-dev
arn:aws:s3:::aws-athena-query-results-eu-west-1-554360978219
arn:aws:s3:::aws-cloudtrail-logs-554360978219-3a8b3014
arn:aws:s3:::aws-cloudtrail-logs-554360978219-f7b6fe5a
arn:aws:s3:::aws-glue-assets-554360978219-eu-west-1
arn:aws:s3:::aws-glue-scripts-554360978219-eu-west-1
arn:aws:s3:::aws-glue-temporary-554360978219-eu-west-1
arn:aws:s3:::cf-templates-fdjqy3cf0nlh-eu-west-1
arn:aws:s3:::revinax-data-shared
arn:aws:s3:::revinax-handbook-analytics-dev
arn:aws:s3:::revinax-handbook-backup
arn:aws:s3:::revinax-handbook-data-altprod
arn:aws:s3:::revinax-handbook-data-backup
arn:aws:s3:::revinax-handbook-data-dev
arn:aws:s3:::revinax-handbook-data-prod
arn:aws:s3:::revinax-handbook-data-release
arn:aws:s3:::revinax-handbook-data-shared
arn:aws:s3:::revinax-handbook-reports
arn:aws:s3:::revinax-handbook-web-serverless-dev
arn:aws:s3:::revinax-handbook-web-serverless-prod
arn:aws:s3:::revinax-production-data-archiver
arn:aws:s3:::revinax-webapp-dev-20191007150241-deployment
arn:aws:s3:::revinax-webapp-dev-20191007150522-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151319-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151419-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152232-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152434-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152734-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152924-deployment
arn:aws:s3:::revinax-webapp-prod-20191011151758-deployment
arn:aws:s3:::revinax-webapp-prod-20191011152156-deployment
arn:aws:s3:::revinax-webapp-prod-20191011172617-deployment
arn:aws:s3:::revinaxauthverificationbucket-dev
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-altprod
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-dev
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-jacquelyn
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-master
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-prod
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-release
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-renelle
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-staging
arn:aws:s3:::revinaxwebapp60aee946verificationbucket-prod
arn:aws:s3:::share2.revinax.net

## AWS_S3_004
Set retention policy on S3 buckets
arn:aws:s3:::amplify-amplify-js-app-dev-171633-deployment
arn:aws:s3:::amplify-amplify-js-app-prod-152716-deployment
arn:aws:s3:::amplify-amplify-js-app-staging-151645-deployment
arn:aws:s3:::amplify-amplifytest-dev-150111-deployment
arn:aws:s3:::amplify-js-app-data
arn:aws:s3:::amplify-js-app-dataapp-dev
arn:aws:s3:::amplify-js-app-dataapp-prod
arn:aws:s3:::amplify-revinax-handbook-altprod-161543-deployment
arn:aws:s3:::amplify-revinax-handbook-dd-174702-deployment
arn:aws:s3:::amplify-revinax-handbook-dev-161708-deployment
arn:aws:s3:::amplify-revinax-handbook-master-161045-deployment
arn:aws:s3:::amplify-revinax-handbook-prod-140109-deployment
arn:aws:s3:::amplify-revinax-handbook-release-194445-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-115624-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-150330-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-153209-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163753-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-163815-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-165959-deployment
arn:aws:s3:::amplify-revinax-webapp-dev-170653-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-101216-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-113921-deployment
arn:aws:s3:::amplify-revinax-webapp-prod-114813-deployment
arn:aws:s3:::authhandbookverificationbucket-dev
arn:aws:s3:::aws-athena-query-results-eu-west-1-554360978219
arn:aws:s3:::aws-cloudtrail-logs-554360978219-3a8b3014
arn:aws:s3:::aws-cloudtrail-logs-554360978219-f7b6fe5a
arn:aws:s3:::aws-glue-assets-554360978219-eu-west-1
arn:aws:s3:::aws-glue-scripts-554360978219-eu-west-1
arn:aws:s3:::aws-glue-temporary-554360978219-eu-west-1
arn:aws:s3:::cf-templates-fdjqy3cf0nlh-eu-west-1
arn:aws:s3:::revinax-data-shared
arn:aws:s3:::revinax-handbook-analytics
arn:aws:s3:::revinax-handbook-analytics-dev
arn:aws:s3:::revinax-handbook-backup
arn:aws:s3:::revinax-handbook-data
arn:aws:s3:::revinax-handbook-data-altprod
arn:aws:s3:::revinax-handbook-data-backup
arn:aws:s3:::revinax-handbook-data-dev
arn:aws:s3:::revinax-handbook-data-prod
arn:aws:s3:::revinax-handbook-data-release
arn:aws:s3:::revinax-handbook-data-shared
arn:aws:s3:::revinax-handbook-reports
arn:aws:s3:::revinax-handbook-web-serverless-dev
arn:aws:s3:::revinax-handbook-web-serverless-prod
arn:aws:s3:::revinax-production-data-archiver
arn:aws:s3:::revinax-webapp-dev-20191007150241-deployment
arn:aws:s3:::revinax-webapp-dev-20191007150522-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151319-deployment
arn:aws:s3:::revinax-webapp-dev-20191007151419-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152232-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152434-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152734-deployment
arn:aws:s3:::revinax-webapp-dev-20191007152924-deployment
arn:aws:s3:::revinax-webapp-prod-20191011151758-deployment
arn:aws:s3:::revinax-webapp-prod-20191011152156-deployment
arn:aws:s3:::revinax-webapp-prod-20191011172617-deployment
arn:aws:s3:::revinaxauthverificationbucket-dev
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-altprod
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-dev
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-jacquelyn
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-master
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-prod
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-release
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-renelle
arn:aws:s3:::revinaxhandbookd098ed29verificationbucket-staging
arn:aws:s3:::revinaxwebapp60aee946verificationbucket-prod
arn:aws:s3:::share2.revinax.net